## Sheet1
Project Name
Team Members (Initials) |  |  | Hanith Vijai VELMURUGAN | Alfred YAVOURBE
Sr. No | Milestone | Task | Task Breakdown/Details | Task Owner (Initials) | Dependency (on other task/tasks) | Progress | Task Complition Percentage | Comments
1 | M1: Foundation | Bibliography | Source 12+ post-2021 papers; format in template. | GM |  | Completed | 100% | 18 papers sourced, verified, formatted in APA style
2 | M1: Foundation | Repo Setup | Deliverables folder ready; Prof added. | PT (Lead) |  | Completed | 100% | Deliverables folder created in Teams channel
3 | M1: Foundation | Threat Model | VM: Draft scenarios; PT: Lit alignment; GM: Dataset alignment; EW: Quantum mapping. | VM | Bib. | Completed | 100% | Covers heap spraying, /proc injection, and credential scraping. Grounded in literature
4 | M2: Lit Review | LR Outline | PT: Design structure; VM: Attack section; GM: ML section; EW: Quantum section. | PT | Bib. | Completed | 100% | Submitted May 18. Feedback received and addressed
5 | M2: Lit Review | Completed Lit Review | Full academic literature review addressing professor feedback on quantum limitations. | PT (Lead) | LR Outline | Completed | 100% | Submitted May 29. All 18 papers cited. Quantum critical assessment added
6 | M2: Lit Review | Dataset Prep | GM: Clean features; VM: Map memory signals; PT: Labeling; EW: Q-encoding prep. | GM | LR Outline | Completed | 100% | UNSW-NB15 selected, features identified and documented in thesis
7 | M3: Prototype | ML Pipeline | GM: Isolation Forest; VM: Logic validation; PT: Metrics; EW: Baseline testing. | GM | Dataset | Completed | 100% | Isolation Forest pipeline designed and documented in thesis. Architecture validated against literature
8 | M4: MVP Sprint | Quantum Exp. | EW: Develop Qiskit circuit; GM: Integration; VM/PT: Benchmark runs. | EW | ML Pipe. | Completed | 100% | ZZFeatureMap quantum kernel experiment designed and documented. Results reported in thesis
9 | M4: MVP Sprint | Comp. Analysis | EW: Accuracy comparison; PT: Trade-off analysis; GM: Latency; VM: HW feasibility. | EW | Q-Exp. | Completed | 100% | Classical vs quantum comparison completed. FPR, Recall, F1, AUROC reported in thesis
10 | M5: Final | Thesis/GenAI | PT: Merge doc; VM: Intro/Design; GM: ML Results; EW: Q-Results; All: GenAI report. | PT | All | Completed | 100% | Thesis submitted June 22. GenAI document prepared and attached. Thesis evaluation received
11 | M5: Final | Live Monitor | VM: /proc polling; GM/EW/PT: Test detection lag and real-time inference. | VM | ML Pipe. | Not Started | 0% | Optional stretch goal. Not implemented due to time constraints

## Sheet2
Completed
In Progress
Pending