## Task Tracker
MemoryWatch — Task Tracker
Quantum-Inspired Anomaly Detection for Memory-Based IDS • 6-Week MVP Schedule
Week | Owner | Task | Dependency | Status | Progress % | Due (end of) | Notes
Week 1 | Esala | Create Git repo, branch strategy, shared env file, skeleton entry point | — | Not Started | 0% | Week 1
Week 1 | Esala | Pin versions (Python, scikit-learn, Qiskit 2.x); write README setup | — | Not Started | 0% | Week 1
Week 1 | Ghita | Download UNSW-NB15; confirm 49 features & 9 attack categories; document schema | — | Not Started | 0% | Week 1
Week 1 | Ghita | Write reproducible loader logging rows/class counts/missing values | — | Not Started | 0% | Week 1
Week 1 | Prachin | Prototype minimal Isolation Forest on toy data to validate sklearn setup | — | Not Started | 0% | Week 1
Week 1 | Vignesh | Build threat-to-feature traceability table (3 attack types → signals) | — | Not Started | 0% | Week 1
Week 2 | Esala | Define model interface contract (input shape, score output) | W1 repo | Not Started | 0% | Week 2
Week 2 | Ghita | Implement cleaning, encoding, scaling (Chua et al. workflow) | W1 loader | Not Started | 0% | Week 2
Week 2 | Ghita | Seeded train/test split + selected feature subset | W1 loader | Not Started | 0% | Week 2
Week 2 | Prachin | Agree array interface; stub model class against contract | W2 contract | Not Started | 0% | Week 2
Week 2 | Vignesh | Implement metrics module: FPR, recall, F1 (accuracy secondary) | — | Not Started | 0% | Week 2
Week 3 | Esala | Support integration of baseline into entry point; review classical PR | W3 baseline | Not Started | 0% | Week 3
Week 3 | Ghita | Expose preprocessing as single callable returning train/test arrays | W2 split | Not Started | 0% | Week 3
Week 3 | Prachin | Implement full Isolation Forest pipeline (fit, score, label) | W2 arrays | Not Started | 0% | Week 3
Week 3 | Prachin | Implement dynamic threshold (Shamim et al.) as parameter | W2 arrays | Not Started | 0% | Week 3
Week 3 | Vignesh | Wrap classical model in evaluation harness; first baseline metrics | W3 baseline | Not Started | 0% | Week 3
Week 4 | Esala | Build quantum layer: ZZFeatureMap kernel + One-Class SVM (Qiskit) | W2 arrays | Not Started | 0% | Week 4
Week 4 | Esala | Apply dimensionality reduction / small feature budget for simulation | W4 quantum | Not Started | 0% | Week 4
Week 4 | Ghita | Provide reduced-feature variant for quantum layer | W2 split | Not Started | 0% | Week 4
Week 4 | Prachin | Stabilise baseline; add unit tests; document score ranges | W3 baseline | Not Started | 0% | Week 4
Week 4 | Vignesh | Extend harness to accept quantum scores (identical metrics) | W4 quantum | Not Started | 0% | Week 4
Week 5 | Esala | Hand quantum scores to evaluation; tune feature count & threshold | W4 quantum | Not Started | 0% | Week 5
Week 5 | Ghita | Debug data-related metric anomalies; document dataset limitations | — | Not Started | 0% | Week 5
Week 5 | Prachin | Feed classical scores to harness; tune threshold (FPR vs recall) | W3 baseline | Not Started | 0% | Week 5
Week 5 | Vignesh | Produce classical-vs-quantum comparison table & plots | W4 + W3 scores | Not Started | 0% | Week 5
Week 6 | Esala | Merge all slices into runnable MVP; assemble final report; lead dry-run | All | Not Started | 0% | Week 6
Week 6 | Ghita | Write data/preprocessing report section; verify clean rerun | — | Not Started | 0% | Week 6
Week 6 | Prachin | Write classical-model report section; support integration & demo | — | Not Started | 0% | Week 6
Week 6 | Vignesh | Write evaluation/results sections; prepare results slides | W5 comparison | Not Started | 0% | Week 6

## Dashboard
MemoryWatch — Progress Dashboard
Live rollup from the Task Tracker (auto-calculated)
Overall Progress
Total tasks | 29
Done | 0
In Progress | 0
Blocked | 0
Not Started | 29
Avg completion % | 0%
Progress by Member
Member | Tasks | Done | Avg %
Esala | 8 | 0 | 0%
Ghita | 8 | 0 | 0%
Prachin | 7 | 0 | 0%
Vignesh | 6 | 0 | 0%
Progress by Week
Week | Tasks | Done | Avg %
Week 1 | 6 | 0 | 0%
Week 2 | 5 | 0 | 0%
Week 3 | 5 | 0 | 0%
Week 4 | 5 | 0 | 0%
Week 5 | 4 | 0 | 0%
Week 6 | 4 | 0 | 0%

## Milestones
MemoryWatch — Milestones & Deliverables
Critical path: Data (W2) → Classical (W3) → Quantum (W4) → Comparison (W5) → Integration (W6)
Week | Milestone | Definition of Done | Status | Progress %
Week 1 | Setup & data foundation | Repo, env, dataset loaded; threat-to-feature mapping locked | Not Started | 0%
Week 2 | Preprocessing pipeline | Clean/encode/scale; reproducible split; feature subset selected | Not Started | 0%
Week 3 | Classical baseline (MVP core) | Isolation Forest end to end with dynamic threshold | Not Started | 0%
Week 4 | Quantum layer | ZZFeatureMap kernel + One-Class SVM on same data | Not Started | 0%
Week 5 | Evaluation & comparison | FPR/recall/F1 for both; comparison table & plots | Not Started | 0%
Week 6 | Integration, report & demo | Unified MVP, final report, slides, dry-run done | Not Started | 0%

## Deliverables
MemoryWatch — Final Deliverables Checklist
Tick off before submission
Deliverable | Owner | Done?
Runnable MVP repo (single command/notebook) + README + pinned env | Esala | No
Preprocessing module + reproducible UNSW-NB15 split | Ghita | No
Isolation Forest baseline with dynamic thresholding | Prachin | No
Quantum layer (ZZFeatureMap + One-Class SVM, Qiskit simulation) | Esala | No
Evaluation outputs: FPR/recall/F1 + comparison table & plots | Vignesh | No
Final written report (all sections merged, consistent references) | Esala | No
Presentation slides + completed dry-run | All | No